## Cover
ABC-MS
TASKLIST
| Project Code | ABC-MS
Document Code

## Tasklist (hidden)
PROJECT TASKLIST
No | Task | Resource | Planned Start date | PlannedEnd date | Planned efforts (hours)
1 | <Requirements Development & Management> |  |  |  |  | Project Duration:
2 | <REQ Study&Create - RM Sheet/Requirement Understanding Document> |  |  |  |  | Starts: |  | yyyy/mm/dd
3 | <REQ Reviews - RM Sheet/Requirement Understanding Document> |  |  |  |  | Ends: |  | yyyy/mm/dd
4 | <REQ Correct - RM Sheet/Requirement Understanding Document>
5 | <REQ Translate - RM Sheet/Requirement Understanding Document> |  |  |  |  | Holidays:
6 | <REQ Study&Create - URD/SRS> |  |  |  |  | R2S:
7 | <REQ Reviews - URD/SRS> |  |  |  |  | - Independent Day ( 2-Sep) | - <____Holidays 1____ yyyy/mm/dd>
8 | <REQ Correct - URD/SRS> |  |  |  |  | - FPT Foundation Day (13-Sep) | - <____Holidays 2____ yyyy/mm/dd ~ yyyy/mm/dd>
9 | <REQ Translate - URD/SRS> |  |  |  |  | Customer:
10 | <DAR> | [5 empty] | - <____Holidays 1____ yyyy/mm/dd>
11 | <DAR Create DAR evaluation for technical > | [5 empty] | - <____Holidays 2____ yyyy/mm/dd ~ yyyy/mm/dd>
12 | <DAR review DAR report>
13 | <DAR Correct DAR report> |  |  |  |  | Deliverables:
14 | <Design> |  |  |  |  | yyyy/mm/dd: Deliver Function Specification
15 | <DES Study&Create - Architectural Design> |  |  |  |  | yyyy/mm/dd: Deliver Detail Design
16 | <DES Reviews - Architectural Design> |  |  |  |  | yyyy/mm/dd: Deliver Interim Source I
17 | <DES Correct - Architectural Design> |  |  |  |  | yyyy/mm/dd: Deliver Interim PCL - Program Test
18 | <DES Translate - Architectural Design> |  |  |  |  | yyyy/mm/dd: Deliver Interim PCL - Total Test
19 | <DES Study&Create - Detail Design> |  |  |  |  | yyyy/mm/dd: Deliver Interim Source II
20 | <DES Reviews - Detail Design> |  |  |  |  | yyyy/mm/dd: Deliver Acceptance Test Release
21 | <DES Correct - Detail Design> |  |  |  |  | yyyy/mm/dd: Deliver Final Release
22 | <DES Translate - Detail Design>
23 | <Coding>
24 | <COD Create Source code>
25 | <COD Review Code>
26 | <COD Correct review code defects>
27 | <COD Correct UT defects>
28 | <COD Correct IT/ST defects>
29 | <Unit Test>
30 | <UT Create UT cases>
31 | <UT Review UT cases>
32 | <UT Execute UT cases>
33 | <UT Correct UT cases>
34 | <UT Translate UT cases>
35 | <Integration Test / System Test>
36 | <ITST Create ITST cases>
37 | <ITST Review ITST cases>
38 | <ITST Execute ITST cases>
39 | <ITST Correct ITST cases>
40 | <ITST Translate ITST cases>
41 | <Product Integration>
42 | <PI Integrate package 1>
43 | <PI Integrate package 2>
44 | <Deployment>
45 | <DEP Deploy package>
46 | <DEP Create release note>
47 | <Customer Support>
48 | <CS Create Support plan>
49 | <CS Support customer>
50 | <CS Create Support report>
51 | <Project planning>
52 | <Hold Pre-Planning Meeting>
53 | <Establish Project Infrastructure>
54 | <Review Project Inputs>
55 | <Validate Acceptance Criteria>
56 | <Estimate - Create>
57 | <Estimate - Review>
58 | <Estimate - Approve>
59 | <Identify Project Risks>
60 | <Work Order - Create, Approve>
61 | <Hold Project Kick-Off Meeting>
62 | <Develop Staff Management (HR Plan)>
63 | <Define Measurement Plan>
64 | <Compile Project Plan (IPM Plan) - Create>
65 | <Compile Project Plan (IPM Plan) - Review>
66 | <Compile Project Plan (IPM Plan) - Approve>
67 | <Project schedule - Create>
68 | <Estimate & Project Plan - Update for change or new stage>
69 | <Estimate & Project Plan updated - Review>
70 | <Estimate & Project Plan updated - Approve>
71 | <Perform Project management tasks>
72 | <Task 1>
73 | <Task 2>
74 | <Project Monitoring and Control>
75 | <Weekly report>
76 | <Weekly meeting with Project Team>
77 | <Weekly meeting with Senior Manager>
78 | <Milestone review>
79 | <Actions to resolve issues, risks>
80 | <Training>
81 | <Perform training course 1>
82 | <Perform training course 2>
83 | <Configuration Management and Data Management>
84 | <CM Plan - Create>
85 | <CM Plan - Review>
86 | <CM Plan - Approve>
87 | <Perform CM & DM tasks>
88 | <Baseline status (at least once every 2 months)>
89 | <CM audit (in PCV)>
90 | <Communication and Translation>
91 | <Task 1>
92 | <Task 2>
93 | <M&A and QPM>
94 | <Maintain QPPO (established in Measurement Plan)>
95 | <Project PPM - Establish>
96 | <Collect metric data>
97 | <Project PPM - Calibrate>
98 | <Quality Assurance>
99 | <Perform actions from PCV observation and audit>
100 | <Internal Audit>
101 | <CAR>
102 | <Collect problems>
103 | <Analyze root cause and propose action>
104 | <Implement action>
105 | <Evaluate effect>
106 | <Others>
107 | Total

## Record of change (hidden)
RECORD OF CHANGE
No | Effective Date | Version | Change Description | Reason | Reviewer | Approver
1 | <dd/mmm/yy> | <x.y> | <Describe the change of document in detail> | <Describe reason for the change>
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Tasklist_Schedule
PROJECT TASKLIST
No | Task | Resource | Planned Start date | PlannedEnd date | Planned efforts (hours) | Status | Actual end date | Actual effort (h)
| <Management> | [7 empty] | Project Duration:
| Project kick off meeting | Cuong Pham | 2021-07-01 | 2021-07-01 | 1 | Done | 2021-07-01 | 1 | Starts: | 2021-07-01
| #REF! | #REF! | 2021-07-01 | 2021-07-01 | 1 | Done | 2021-07-01 | 1 | Ends: | 2021-07-05
| #REF! | #REF! | 2021-07-01 | 2021-07-01 | 1 | Done | 2021-07-01 | 1
| #REF! | #REF! | 2021-07-01 | 2021-07-01 | 1 | Done | 2021-07-01 | 1 | Holidays:
| #REF! | #REF! | 2021-07-01 | 2021-07-01 | 1 | Done | 2021-07-01 | 1 | R2S:
Deliverables:
20-June-2021: Deliver SRS
2-July-16: Deliver Architecture Design & Detail Design
4-July-17: Deliver Final Source Code & ST report
<Requirements>
| REQ Study - Understanding documents for Mobile Store SRS | <user account> | 2021-07-01 | 2021-07-01 | 4 | Done | 2016-12-09 | 4
|  |  | 2021-07-01 | 2021-07-01
|  |  | 2021-07-01 | 2021-07-01
|  |  | 2021-07-01 | 2021-07-01
|  |  | 2021-07-01 | 2021-07-01
| #REF! | #REF! | 2021-07-01 | 2021-07-01 | 3 | Done | 2016-12-13 | 3
| #REF! | #REF! | 2021-07-01 | 2021-07-01 | 3 | Done | 2016-12-13 | 3
| #REF! | #REF! | 2021-07-01 | 2021-07-01 | 3 | Done | 2016-12-13 | 3
| #REF! | #REF! | 2021-07-01 | 2021-07-01 | 4.5 | Done | 2016-12-14 | 4.5
| #REF! | #REF! | 2021-07-01 | 2021-07-01 | 4.5 | Done | 2016-12-14 | 4.5
| #REF! | #REF! | 2021-07-01 | 2021-07-01 | 4.5 | Done | 2016-12-14 | 4.5
| #REF! | #REF! | 2021-07-01 | 2021-07-01 | 4.5 | Done | 2016-12-14 | 4.5
| #REF! | #REF! | 2021-07-01 | 2021-07-01 | 4.5 | Done | 2016-12-14 | 4.5
| REQ Correction - Correct SRS review defects | <user account> | 2021-07-01 | 2021-07-01 | 12 | Done | 2016-12-16 | 12
<Design>
| DES Study - Architectural Design … | <user account> | 2016-12-15 | 2016-12-19 | 9 | Done | 2016-12-19 | 9
| DES Create - Detail Design for classes | <user account> | 2016-12-20 | 2016-12-23 | 9 | Done | 2016-12-23 | 9
| DES Create - Detail Design for screens | <user account> | 2016-12-20 | 2016-12-23 | 9 | Done | 2016-12-23 | 9
| DES Reviews - Architectural Design group review | <user account> | 2016-12-20 | 2016-12-20 | 0.5 | Done | 2016-12-20 | 0.5
| DES Reviews - Review Detail Design checklist review | <user account> | 2016-12-20 | 2016-12-20 | 1 | Done | 2016-12-20 | 1
| DES Correction - Correct Architectural Design review defects | <user account> | 2016-12-20 | 2016-12-21 | 3 | Done | 2016-12-21 | 3
<Coding>
| COD Create database script to generate DDMF database structure | <user account> | 2016-12-26 | 2016-12-27 | 14 | Done | 2016-12-27 | 14
| COD Create database triggers for … | <user account> | 2016-12-28 | 2016-12-28 | 12 | Done | 2016-12-28 | 12
| COD Create database triggers for … | <user account> | 2016-12-28 | 2016-12-28 | 12 | Done | 2016-12-28 | 12
| COD Create Source code for Use Case: … | <user account> | 2016-12-26 | 2016-12-27 | 12 | Done | 2016-12-27 | 12
| COD Create deployment guideline | <user account> | 2017-01-05 | 2017-01-09 | 3 | Done | 2017-01-09 | 3
<COD Review Code>
| COD Review Code - … | <user account> | 2016-12-27 | 2016-12-27 | 1 | Done | 2016-12-27 | 1
| COD Review Code - … | <user account> | 2017-01-11 | 2017-01-12 | 8 | Done | 2017-01-12 | 8
<COD Correct review code defects>
| COD Correction - Correct review code defects… | <user account> | 2017-01-11 | 2017-01-12 | 7 | Done | 2017-01-12 | 7
<COD Correct UT defects>
| COD Correction - Correct UT defects… | <user account> | 2017-01-24 | 2017-01-25 | 8 | Done | 2017-01-25 | 8
<COD Correct IT/ST defects>
| COD Correction - Correct ST defects .. | <user account> | 2017-02-09 | 2017-02-10 | 7 | Done | 2017-02-10 | 7
<Unit Test>
| UT Creation - Source code for Use Case: Pre-flight Check for ASB-Supplement-AMOC | <user account> | 2017-01-13 | 2017-01-13 | 8 | Done | 2017-01-13 | 8
|  | <user account> | 2017-01-19 | 2017-01-19 | 7 | Done | 2017-01-19 | 7
|  | <user account> | 2017-01-20 | 2017-01-20 | 2 | Done | 2017-01-20 | 2
| UT Execute UT cases | <user account> | 2017-01-20 | 2017-01-24 | 17.5 | Done | 2017-01-24 | 17.5
<System Test>
| ST Creation - ST for Use Case: … | <user account> | 2016-12-20 | 2016-12-20 | 8 | Done | 2016-12-20 | 8
| ST Review ST case - Group review | <user account> | 2017-01-25 | 2017-01-26 | 5 | Done | 2017-01-26 | 5
|  | <user account> | 2017-02-02 | 2017-02-06 | 8 | Done | 2017-02-06 | 8
|  | <user account> | 2017-02-03 | 2017-02-08 | 16 | Done | 2017-02-08 | 16
|  | <user account> | 2017-02-03 | 2017-02-08 | 16 | Done | 2017-02-08 | 16
QA task
| Project Opening Tasks | LanLT2 | 2016-12-09 | 2016-12-09 | 3 | Done | 2016-12-09 | 3
| Weekly task checking and reminder | LanLT2 | 2016-12-16 | 2016-12-16 | 3 | Done | 2016-12-16 | 3
| Project Weekly PCV | LanLT2 | 2016-12-16 | 2016-12-16 | 2 | Done | 2016-12-16 | 2
| Weekly Monitoring Report | LanLT2 | 2016-12-16 | 2016-12-16 | 1.5 | Done | 2016-12-16 | 1.5
| Final Inspection for SRS | LanLT2 | 2016-12-16 | 2016-12-16 | 3 | Done | 2016-12-16 | 3
| Project Tasklist | LanLT2 | 2016-12-16 | 2016-12-16 | 3 | Done | 2016-12-16 | 3
| Wrap up baseline | LanLT2 | 2017-02-13 | 2017-02-13 | 2 | Done | 2017-02-13 | 2
| Project Closure Effort | LanLT2 | 2017-02-14 | 2017-02-14 | 3 | Done | 2017-02-14 | 3

## Tasklist (2)
PROJECT TASKLIST
No | Task | PIC | 2021-07-01 | [22 empty] | 2021-08-01 | [30 empty] | 2021-09-01
 | time axis 2016-12-09 to 2017-02-24
<Management>
| Project kick off meeting | <user account> | bar: 2016-12-14
<Requirements>
1 | REQ Study - Understanding documents for Mobile Store SRS | <user account> | 2016-12-09: 4
2 | REQ Study - Understanding documents for Mobile Store SRS | <user account> | 2016-12-09: 4
3 | REQ Study - Understanding documents for Mobile Store SRS | <user account> | 2016-12-09: 4
4 | REQ Study - Understanding documents for Mobile Store SRS | <user account> | 2016-12-09: 4
5 | REQ Study - Understanding documents for Mobile Store SRS | <user account> | 2016-12-09: 3; 2016-12-12: 1
6 | REQ Study - Understanding documents for Mobile Store SRS | <user account> | 2016-12-09: 3; 2016-12-12: 1
7 | REQ Study - Understanding documents for Mobile Store SRS | <user account> | 2016-12-09: 3; 2016-12-12: 1
8 | REQ Study - Understanding documents for Mobile Store SRS | <user account> | 2016-12-09: 3; 2016-12-12: 1
9 | REQ Study - Understanding documents for Mobile Store SRS | <user account> | 2016-12-12: 6
10 | REQ Study - Understanding documents for Mobile Store SRS | <user account> | 2016-12-12: 6
| REQ Correction - Correct SRS review defects | <user account> | 2016-12-14: 2; 2016-12-15: 8; 2016-12-16: 4
<Design>
| DES Study - Architectural Design … | <user account> | 2016-12-15: 3; 2016-12-16: 4; 2016-12-19: 3
| DES Study - Architectural Design … | <user account> | 2016-12-15: 4.5; 2016-12-16: 4; 2016-12-19: 4
| DES Study - Architectural Design … | <user account> | 2016-12-15: 3; 2016-12-16: 3; 2016-12-19: 4
| DES Create - Architectural Design | <user account> | 2016-12-15: 4; 2016-12-16: 3; 2016-12-19: 4
| DES Create - Architectural Design | <user account> | 2016-12-15: 3; 2016-12-16: 3; 2016-12-19: 4
| DES Create - Architectural Design | <user account> | 2016-12-15: 5; 2016-12-16: 4; 2016-12-19: 4
| DES Study - Detail Design for database | <user account> | 2016-12-20: 3; 2016-12-21: 3; 2016-12-22: 3; 2016-12-23: 1.5
| DES Study - Detail Design for classes | <user account> | 2016-12-20: 2.5; 2016-12-21: 3; 2016-12-22: 3; 2016-12-23: 2
| DES Study - Detail Design for screens | <user account> | 2016-12-20: 3; 2016-12-21: 3; 2016-12-22: 3; 2016-12-23: 2
| DES Create - Detail Design for database | <user account> | 2016-12-20: 3.5; 2016-12-21: 2.5; 2016-12-22: 3; 2016-12-23: 1.5
| DES Create - Detail Design for classes | <user account> | 2016-12-20: 3.5; 2016-12-21: 3; 2016-12-22: 4; 2016-12-23: 2
| DES Create - Detail Design for screens | <user account> | 2016-12-20: 3.5; 2016-12-21: 3; 2016-12-22: 4; 2016-12-23: 2
| DES Reviews - Architectural Design group review | <user account> | 2016-12-20: 0.5
| DES Reviews - Architectural Design group review | <user account> | 2016-12-20: 0.5
| DES Reviews - Architectural Design group review | <user account> | 2016-12-20: 0.5
| DES Reviews - Architectural Design group review | <user account> | 2016-12-20: 0.5
| DES Reviews - Architectural Design checklist review | <user account> | 2016-12-19: 0.5; 2016-12-21: 0.5
| DES Reviews - Review Detail Design group review | <user account> | 2016-12-23: 2.5
| DES Reviews - Review Detail Design group review | <user account> | 2016-12-23: 2.5
| DES Reviews - Review Detail Design group review | <user account> | 2016-12-23: 2.5
| DES Reviews - Review Detail Design group review | <user account> | 2016-12-23: 2.5
| DES Reviews - Review Detail Design checklist review | <user account> | 2016-12-20: 0.5; 2016-12-26: 0.5
| DES Correction - Correct Architectural Design review defects | <user account> | 2016-12-20: 0.5; 2016-12-21: 2
| DES Correction - Correct Architectural Design review defects … | <user account> | 2016-12-20: 0.5; 2016-12-21: 2
| DES Correction - Correct Architectural Design review defects … | <user account> | 2016-12-20: 1; 2016-12-21: 2
| DES Correction - Correct Database Detail Design review defects | <user account> | 2016-12-23: 2; 2016-12-26: 1
| DES Correction - Correct Classes Detail Design review defects | <user account> | 2016-12-23: 1; 2016-12-26: 4
| DES Correction - Correct Screens Detail Design review defects | <user account> | bar: 2016-12-23
<Coding>
| COD Create database script to generate DDMF database structure | <user account> | 2016-12-26: 6.5; 2016-12-27: 7.5
| COD Create database triggers for … | <user account> | 2016-12-28: 7
| COD Create database triggers for … | <user account> | 2016-12-28: 6.3
| COD Create Source code for Use Case: … | <user account> | 2016-12-26: 4; 2016-12-27: 7.3
|  | <user account> | 2016-12-28: 7.4
|  | <user account> | 2016-12-26: 8; 2016-12-27: 7.5
|  | <user account> | 2016-12-29: 8; 2016-12-30: 7.5
|  | <user account> | 2016-12-29: 8; 2016-12-30: 7.5
|  | <user account> | 2016-12-29: 8; 2016-12-30: 7.5
|  | <user account> | 2017-01-02: 7; 2017-01-03: 6
|  | <user account> | 2017-01-02: 6
|  | <user account> | 2017-01-02: 7; 2017-01-03: 6
|  | <user account> | 2017-01-04: 8; 2017-01-05: 7
|  | <user account> | 2017-01-04: 7; 2017-01-05: 7
|  | <user account> | 2017-01-03: 7; 2017-01-04: 7
|  | <user account> | 2017-01-05: 6; 2017-01-06: 6
|  | <user account> | 2017-01-06: 7; 2017-01-09: 3
|  | <user account> | 2017-01-06: 6
|  | <user account> | 2017-01-09: 6
| COD Create deployment guideline | <user account> | bar: 2017-01-05 to 2017-01-06; 2017-01-09
<COD Review Code>
| COD Review Code - … | <user account> | 2016-12-27: 0.5
| COD Review Code - … | <user account> | 2016-12-27: 0.5
| COD Review Code - … | <user account> | 2016-12-27: 0.5
| COD Review Code - … | <user account> | 2016-12-27: 0.5
| COD Review Code - … | <user account> | 2017-01-10: 5; 2017-01-11: 5
| COD Review Code - … | <user account> | 2017-01-10: 8; 2017-01-11: 2
| COD Review Code - … | <user account> | 2017-01-10: 5; 2017-01-11: 5
| COD Review Code - … | <user account> | 2017-01-10: 5; 2017-01-11: 5
| COD Review Code - … | <user account> | 2017-01-11: 3; 2017-01-12: 3
<COD Correct review code defects>
| COD Correction - Correct review code defects… | <user account> | 2017-01-11: 2; 2017-01-12: 5
| COD Correction - Correct review code defects… | <user account> | 2017-01-12: 8
| COD Correction - Correct review code defects… | <user account> | 2017-01-12: 8
<COD Correct UT defects>
| COD Correction - Correct UT defects… | <user account> | 2017-01-24: 3; 2017-01-25: 5.5
| COD Correction - Correct UT defects… | <user account> | 2017-01-25: 6
| COD Correction - Correct UT defects… | <user account> | 2017-01-24: 3; 2017-01-25: 5.5
<COD Correct IT/ST defects>
| COD Correction - Correct ST defects .. | <user account> | 2017-02-09: 5; 2017-02-10: 2
| COD Correction - Correct ST defects… | <user account> | 2017-02-09: 7; 2017-02-10: 2
| COD Correction - Correct ST defects… | <user account> | 2017-02-09: 6; 2017-02-10: 2
<Unit Test>
| UT Creation - Source code for Use Case: Pre-flight Check for ASB-Supplement-AMOC | <user account> | 2017-01-13: 8
|  | <user account> | 2017-01-13: 8
|  | <user account> | 2017-01-13: 8
|  | <user account> | 2017-01-13: 8
|  | <user account> | 2017-01-16: 8
|  | <user account> | 2017-01-16: 8
|  | <user account> | 2017-01-16: 8
|  | <user account> | 2017-01-16: 8
|  | <user account> | 2017-01-17: 8
|  | <user account> | 2017-01-17: 8
|  | <user account> | 2017-01-17: 8
|  | <user account> | 2017-01-17: 8
|  | <user account> | 2017-01-18: 8
|  | <user account> | 2017-01-18: 8
|  | <user account> | 2017-01-18: 8; 2017-01-19: 5
|  | <user account> | 2017-01-18: 8; 2017-01-19: 5
|  | <user account> | 2017-01-19: 6.5
|  | <user account> | 2017-01-19: 6.5
| UT Review UT cases - Peer review | <user account> | 2017-01-19: 3; 2017-01-20: 3.5
| UT Review UT cases - Peer review | <user account> | 2017-01-19: 3; 2017-01-20: 3.5
| UT Correct UT cases | <user account> | 2017-01-20: 2.5
| UT Correct UT cases | <user account> | 2017-01-20: 2.5
|  | <user account> | 2017-01-20: 2.5
|  | <user account> | 2017-01-20: 2.5
|  | <user account> | 2017-01-20: 4; 2017-01-23: 8; 2017-01-24: 5
|  | <user account> | 2017-01-20: 4; 2017-01-23: 8; 2017-01-24: 5
|  | <user account> | 2017-01-20: 1; 2017-01-23: 8; 2017-01-24: 8
| UT Execute UT cases | <user account> | 2017-01-20: 1; 2017-01-23: 8; 2017-01-24: 8
<System Test>
| ST Creation - ST for Use Case: … | <user account> | 2016-12-20: 8
| ST Creation - ST for Use Case: … | <user account> | 2016-12-21: 8
|  | <user account> | 2016-12-22: 8
|  | <user account> | 2016-12-23: 8
|  | <user account> | 2016-12-26: 8
|  | <user account> | 2016-12-27: 8
|  | <user account> | 2016-12-28: 8
|  | <user account> | 2016-12-29: 8
|  | <user account> | 2016-12-30: 4
|  | <user account> | 2017-01-02: 4
|  | <user account> | 2017-01-02: 4
|  | <user account> | 2017-01-03: 4
|  | <user account> | 2017-01-03: 4
|  | <user account> | 2017-01-04: 4
|  | <user account> | 2016-12-30: 4
|  | <user account> | 2017-01-04: 4
|  | <user account> | 2017-01-25: 2.5; 2017-01-26: 2.3
|  | <user account> | 2017-01-25: 2.5; 2017-01-26: 2.3
|  | <user account> | 2017-01-25: 2.5; 2017-01-26: 3.1
| ST Review ST case - Group review | <user account> | 2017-01-25: 1; 2017-01-26: 3
| ST Review ST case - Group review | <user account> | 2017-01-25: 2.5; 2017-01-26: 2.3
| ST Correct ST cases | <user account> | 2017-01-26: 2.5
| ST Correct ST cases | <user account> | 2017-01-25: 5.5; 2017-01-26: 4
| ST Execution - Run ST for Use Case:… | <user account> | 2017-02-03: 2; 2017-02-06: 2
| ST Execution - Run ST for Use Case:… | <user account> | 2017-02-09: 4
| ST Execution - Run ST for Use Case:… | <user account> | 2017-02-03: 3
| ST Execution - Run ST for Use Case:… | <user account> | 2017-02-02: 8
| ST Execution - Run ST for Use Case:… | <user account> | 2017-02-03: 7
| ST Execution - Run ST for Use Case:… | <user account> | 2017-02-06: 8
| ST Execution - Run ST for Use Case:… | <user account> | 2017-02-07: 8
| ST Execution - Run ST for Use Case:… | <user account> | 2017-02-08: 8
|  | <user account> | 2017-01-26: 4; 2017-02-02: 4
|  | <user account> | 2017-01-26: 4; 2017-02-02: 4
|  | <user account> | 2017-01-26: 2; 2017-02-02: 4
|  | <user account> | 2017-02-02: 4; 2017-02-03: 2
|  | <user account> | 2017-02-02: 4; 2017-02-03: 2
|  | <user account> | 2017-02-02: 4; 2017-02-03: 2; 2017-02-06: 2
|  | <user account> | 2017-02-03: 4; 2017-02-06: 4; 2017-02-07: 4; 2017-02-08: 4
|  | <user account> | 2017-02-03: 4; 2017-02-06: 4; 2017-02-07: 4; 2017-02-08: 4

## Check OT
PIC | 2016-12-01 | [22 empty] | 2017-01-01 | [30 empty] | 2017-02-01
 | time axis 2016-12-09 to 2017-02-14
<user account> | 28 | 0 | 0 | 16 | 0 | 3 | 30.5 | 25 | 0 | 0 | 23.5 | 31.5 | 32 | 28 | 33 | 0 | 0 | 32 | 32.3 | 28.7 | 32 | 30.5 | 0 | 0 | 28 | 27 | 30 | 21 | 20 | 0 | 0 | 10 | 23 | 22 | 24 | 32 | 0 | 0 | 32 | 32 | 32 | 29 | 27 | 0 | 0 | 32 | 32 | 33.5 | 29.5 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 26 | 0 | 0 | 20 | 16 | 16 | 22 | 6 | 0 | 0 | 0 | 0
<user account> | 28 | 0 | 0 | 16 | 0 | 3 | 30.5 | 25 | 0 | 0 | 23.5 | 31.5 | 32 | 28 | 33 | 0 | 0 | 32 | 32.3 | 28.7 | 32 | 30.5 | 0 | 0 | 28 | 27 | 30 | 21 | 20 | 0 | 0 | 10 | 23 | 22 | 24 | 32 | 0 | 0 | 32 | 32 | 32 | 29 | 27 | 0 | 0 | 32 | 32 | 33.5 | 29.5 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 26 | 0 | 0 | 20 | 16 | 16 | 22 | 6 | 0 | 0 | 0 | 0
<user account> | 28 | 0 | 0 | 16 | 0 | 3 | 30.5 | 25 | 0 | 0 | 23.5 | 31.5 | 32 | 28 | 33 | 0 | 0 | 32 | 32.3 | 28.7 | 32 | 30.5 | 0 | 0 | 28 | 27 | 30 | 21 | 20 | 0 | 0 | 10 | 23 | 22 | 24 | 32 | 0 | 0 | 32 | 32 | 32 | 29 | 27 | 0 | 0 | 32 | 32 | 33.5 | 29.5 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 26 | 0 | 0 | 20 | 16 | 16 | 22 | 6 | 0 | 0 | 0 | 0
<user account> | 28 | 0 | 0 | 16 | 0 | 3 | 30.5 | 25 | 0 | 0 | 23.5 | 31.5 | 32 | 28 | 33 | 0 | 0 | 32 | 32.3 | 28.7 | 32 | 30.5 | 0 | 0 | 28 | 27 | 30 | 21 | 20 | 0 | 0 | 10 | 23 | 22 | 24 | 32 | 0 | 0 | 32 | 32 | 32 | 29 | 27 | 0 | 0 | 32 | 32 | 33.5 | 29.5 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 26 | 0 | 0 | 20 | 16 | 16 | 22 | 6 | 0 | 0 | 0 | 0
<user account> | 28 | 0 | 0 | 16 | 0 | 3 | 30.5 | 25 | 0 | 0 | 23.5 | 31.5 | 32 | 28 | 33 | 0 | 0 | 32 | 32.3 | 28.7 | 32 | 30.5 | 0 | 0 | 28 | 27 | 30 | 21 | 20 | 0 | 0 | 10 | 23 | 22 | 24 | 32 | 0 | 0 | 32 | 32 | 32 | 29 | 27 | 0 | 0 | 32 | 32 | 33.5 | 29.5 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 26 | 0 | 0 | 20 | 16 | 16 | 22 | 6 | 0 | 0 | 0 | 0